## Overview
LLM Chatbot Feature Baseline
Repository: /Users/huntsyea/Dev/llm-chatbot ¦ Audit date: 2026-06-21 ¦ Branch: main ¦ Canonical workbook
Metric | Value | Notes | Metric | Value | Notes
User stories | 28 | Every current feature is tracked in User Stories. | Fixed defects | 33 | Resolved in source this pass.
Verified stories | 33 | Passed browser/static checks. | Open defects | 0 | Still needs implementation or package updates.
Partial stories | 4 | Some behavior verified, provider/mock coverage remains. | Gated defects | 0 | Requires confirmation before package/delete work.
Blocked stories | 0 | Needs mock harness or explicit provider-call approval. | Blocked defects | 0 | Requires mock harness or approved provider calls.
Static-only stories | 0 | Source reviewed; no runtime fixture yet. | Watch items | 1 | Product or overhaul follow-up decisions.
Latest overhaul update | 2026-07-01 | Next.js exploration workspace rebuild implemented and verified with mock browser flow; live Gateway remains config-dependent. | npm audit low | 0
Build/lint/strict TS | Pass | npm run build, npm run lint, strict tsc all pass. | npm audit moderate | 0
Outdated packages | 0 | npm outdated --json. | npm audit high | 0
Major-version drifts | 0 | Latest major differs from installed major. | npm audit critical | 0
npm audit total | 0 | Final npm audit status. | Docs | Fixed | README and technical-docs.md stale-reference scan passes.
Provider calls | Unavailable | Successful real provider tests could not run because both provider keys are missing.
Canonical status | Current | This file is the single tracking ledger for the baseline audit.
Story Status | Count
Verified | 20
Partial | 2
Blocked | 0
Needs Fix | 0
Static Only | 0
Gated | 0
Not Tested | 0
Defect Status | Count
Open | 0
Fixed | 33
Partial | 0
Gated | 0
Blocked | 0
Watch | 1

## User Stories
Canonical User Stories and Feature Status
Expected behavior is derived from code and verified evidence, not new product assumptions.
ID | Area | Feature | User Story | Expected Behavior | Source Evidence | Status | Test Evidence | Defects / Risks | Priority | Next Action
US-001 | App Shell | Application header and main layout | As a user, I want the Wabbit app shell to load with a clear header and chat workspace so I know the app is ready. | The app renders a centered 'wabbit' header, an input card, model controls, and an empty response carousel region without requiring API keys at startup. | src/App.tsx; src/components/ChatInterface.tsx | Verified | Browser no-env load on http://127.0.0.1:5174/ and dummy-key load on 5173 rendered the shell with no startup crash. |  | P2 | Keep as baseline behavior during overhaul.
US-002 | State | Chat context provider | As the app, I want one chat state provider so responses, loading state, model selection, Gemini config, and active carousel index stay coordinated. | ChatProvider initializes default OpenRouter Llama 3.3, empty responses, loading flags, Gemini defaults, and reducer actions for responses, model, config, and active index. | src/components/ChatContextProvider.tsx; src/hooks/useChatContext.ts | Verified | Model selection, Gemini config, response creation, and active carousel index all changed correctly during browser tests. |  | P2 | Keep reducer small; add tests when a test runner is introduced.
US-003 | Query Input | Empty query state | As a user, I want the query input to show a prompt and avoid submitting blank text so accidental empty requests are prevented. | The textbox uses the placeholder 'What's your next wabbit hole?'; the send button only renders when query.trim() is non-empty. | src/components/QueryInput.tsx | Verified | Browser test: send button count was 0 when empty, 1 after typing 'hello world', and 0 after keyboard clear. Source scan verifies deprecated onKeyPress was removed in favor of onKeyDown. |  | P2 | Keep behavior.
US-004 | Query Input | Manual query submission | As a user, I want to type a question and submit it with Enter or the send button so the selected model returns a response card. | Submit sets loading, stores current query, resolves provider from selectedModel, reads the provider key, calls the registered client, appends a Response, clears input on success, and resets loading. Handled errors render as response cards. | src/components/QueryInput.tsx; src/services/api/ApiClientRegistry.ts | Verified | Final mock-mode browser tests on http://127.0.0.1:5181/ submitted typed OpenRouter and Gemini queries, appended response cards, cleared input on success, and produced no console warnings/errors. npm run verify:user-stories now also covers OpenRouter and Gemini provider-client success paths with deterministic fakes. Real provider success calls were unavailable because provider keys are missing. | Real provider success path still needs real keys. | P1 | Run one real-key smoke test after provider keys are available.
US-005 | Query Input | Recommended query dropdown | As a user, I want a dropdown of suggested prompts so I can start quickly without typing. | The chevron button opens three hardcoded recommendations; selecting an item immediately submits that text through handleSubmit as an override query. | src/components/QueryInput.tsx | Verified | Post-fix browser test opened recommendations, selected a canned query, rendered an OpenRouter mock response card, closed the dropdown, and logged no warnings/errors. | Submit-on-select is a product decision risk; there is no edit-before-send step. | P2 | Decide whether recommendations should submit or only populate input.
US-006 | Models | Model selector dialog | As a user, I want a settings dialog to choose the provider and model used for future chat requests. | The settings icon opens Select Model with OpenRouter and Google Gemini tabs; OpenRouter is selected by default for the default model. | src/components/ModelSelector.tsx; src/components/ModelControls.tsx | Verified | Browser test opened Select Model, saw OpenRouter selected, Google Gemini unselected, and verified closed dialog content is no longer visible after Done. |  | P2 | Keep aria labels on icon controls.
US-007 | Models | OpenRouter model selection | As a user, I want to choose among OpenRouter models so the app can route my next request to that model. | The OpenRouter tab shows three registry-backed radio options and selecting one dispatches SET_MODEL with isGemini=false. | src/lib/models.ts; src/components/ModelSelector.tsx | Verified | Browser test observed Llama 3.3, DeepSeek R1, and Phi-4; Llama 3.3 was checked by default. | Provider model IDs may drift from live provider catalog. | P2 | Refresh model registry during overhaul.
US-008 | Models | Gemini model selection | As a user, I want to choose a Gemini model and see the key requirement so I understand what is needed to use Gemini. | The Gemini tab shows an API-key hint and five Gemini/LearnLM radio options with descriptions; selecting a radio dispatches SET_MODEL with isGemini=true. | src/lib/models.ts; src/components/ModelSelector.tsx | Verified | Browser test observed five Gemini options and selected Gemini 2.0 Flash-Lite. | Some Gemini IDs are experimental or likely stale. | P1 | Validate Google model availability before overhaul implementation.
US-009 | Models | Gemini generation configuration | As a Gemini user, I want to tune temperature, topK, topP, and max output tokens so I can control generation behavior. | The config button appears for the selected Gemini model; the inline config region exposes sliders/input, Apply persists config to context, Done closes the selector, and QueryInput passes config into Gemini generation options. | src/components/GeminiConfigDialog.tsx; src/components/QueryInput.tsx; src/interfaces/core.ts; src/lib/geminiConfig.ts | Verified | Post-fix browser test selected Gemini 2.0 Flash-Lite, changed max output tokens to 1234, applied config, verified Done hides the dialog, submitted a query, and verified response text included maxOutputTokens=1234. npm run verify:user-stories verifies Gemini config defaults, clamps, integer rounding, invalid-input fallback, and Gemini SDK option propagation. | Apply persists config but the inline region remains open until Done; current behavior is documented. | P1 | Keep exact option propagation covered by the deterministic verifier.
US-010 | Models | Central model registry | As a developer, I want models defined in one registry so provider filtering and model lookup remain consistent. | modelRegistry stores name/value/provider/description/config; getModelsByProvider filters by provider and getModelByValue resolves the selected model without importing provider implementations. | src/lib/models.ts; src/interfaces/core.ts | Verified | Source review, selector tests, and npm run verify:user-stories verified registry filtering and lookups. Shared Gemini config types now live in interfaces/core.ts. |  | P2 | Refresh model data as a separate overhaul task.
US-011 | API | API client registry | As a developer, I want provider clients registered behind one interface so UI code can ask for a provider without knowing construction details. | ApiClientRegistryImpl registers gemini/openrouter factories, caches instances by provider and API key, and no provider import throws just because an env key is missing. | src/services/api/ApiClientRegistry.ts; src/api/openRouter.ts; src/api/gemini.ts | Verified | No-env browser startup rendered normally. npm run verify:user-stories verified mock registry providers, cache behavior, deterministic mock content, missing-key factory errors, and deterministic provider-client success paths. | Registry still logs when an unknown provider is requested. | P2 | Keep registry simple; add unit coverage around cache keys later.
US-012 | API | OpenRouter client | As an OpenRouter user, I want the app to send chat-completions requests with my prompt and selected model. | Client posts to OpenRouter chat completions with system/user messages, selected model, temperature, max_tokens, Bearer auth, and wraps empty/API errors without logging keys. | src/api/openRouter.ts | Partial | Final mock-mode OpenRouter query succeeded through the shared registry and rendered markdown/table/code content. No-mock missing-key submit rendered a handled error card. npm run verify:user-stories now asserts the OpenRouter endpoint, model, system/user messages, temperature, max_tokens, Bearer auth header, and returned content using a deterministic axios fake. No successful production call was made because VITE_OPENROUTER_API_KEY is missing. | Production success path needs a real OpenRouter key. | P1 | Run one real-key OpenRouter smoke test after VITE_OPENROUTER_API_KEY is available.
US-013 | API | Gemini client | As a Gemini user, I want the app to send prompts to Google Generative AI with model configuration defaults. | Client constructs GoogleGenerativeAI with the provided API key, applies model and generationConfig, concatenates systemPrompt when present, and wraps empty/API errors. | src/api/gemini.ts | Partial | Mock-mode Gemini query selected gemini-2.0-flash-lite, passed temperature/topK/topP/maxOutputTokens, and rendered response metadata. npm run verify:user-stories now asserts GoogleGenerativeAI construction, selected model, generationConfig, system/user prompt composition, and returned content using a deterministic SDK fake. No Gemini production call made because VITE_GEMINI_API_KEY is missing. | Production success path needs a real Gemini key. | P1 | Run one real-key Gemini smoke test after VITE_GEMINI_API_KEY is available.
US-014 | Responses | Response list and loading state | As a user, I want responses to appear as cards and see pending state while a normal or topic response is loading. | ResponseList maps responses to ChatResponseCard, appends ResponseSkeleton during loading flags, auto-focuses new responses, and shows arrows/dots when multiple cards exist. | src/components/ResponseList.tsx; src/components/ResponseSkeleton.tsx | Verified | Final delayed mock-mode browser test on http://127.0.0.1:5182/ with VITE_MOCK_API_DELAY_MS=1200 showed Loading response skeleton immediately and mid-delay, then replaced it with the final mock response card with no console errors. |  | P1 | Add mock provider latency tests for skeleton behavior.
US-015 | Responses | Card carousel navigation | As a user, I want response cards to be navigable by arrows, keyboard, drag, and indicators when multiple responses exist. | CardCarousel stacks cards by activeIndex, makes inactive slides inert, supports indicator tabs, Previous/Next buttons, ArrowLeft/ArrowRight, wheel navigation, and header drag. | src/components/CardCarousel.tsx; src/components/ResponseList.tsx; src/components/ChatResponseCard.tsx | Verified | Final browser tests verified indicator navigation, Previous and Next icon buttons, no document-level horizontal scroll, response-container scrollLeft=0, active-card topic navigation, and inert inactive card state. | Wheel navigation and autoplay were not separately exercised; autoplay is disabled by current ResponseList usage. | P2 | Add component-level tests for wheel/autoplay only if those remain in product scope.
US-016 | Responses | Response card rendering | As a user, I want each response card to show my query, timestamp, model, and scrollable rendered answer. | ChatResponseCard shows Query or Wabbit Trail label, local time, query/topic title, model row, and MarkdownMessage in a scrollable body. | src/components/ChatResponseCard.tsx; src/components/MarkdownMessage.tsx | Verified | No-env response cards showed query text, timestamp, selected model, and the handled error response body. Missing API keys no longer inject duplicate card warnings. |  | P2 | Keep rendering independent from topic API availability.
US-017 | Markdown | Enhanced markdown rendering | As a user, I want LLM responses to render markdown with headings, code, tables, quotes, links, and copyable code blocks. | EnhancedMarkdown normalizes content, renders react-markdown with GFM, makes headings clickable/keyboard-activatable, adds copy buttons to fenced code blocks, styles tables/quotes/lists, and opens links safely. | src/components/markdown/EnhancedMarkdown.tsx | Verified | Mock-mode markdown fixture rendered headings, a table, and a fenced code block with no leaked node attributes. Copy button is hit-testable; when clipboard write is unavailable, it selects the rendered code block and shows Selected. |  | P2 | Add component tests for headings, code, tables, links, and copy controls.
US-018 | Markdown | Markdown normalization | As a user, I want inconsistent model markdown normalized so responses display consistently. | MarkdownService standardizes underline headings, list markers, tables, script tags, indented/fenced code blocks, and uppercase language tags. | src/services/markdown/MarkdownNormalizer.ts | Verified | Direct normalizer fixture verified underline headings, list marker spacing, table separator formatting, script stripping, indented-to-fenced code, tilde-to-backtick fences, and uppercase language tag normalization. | HTML safety policy is basic script stripping only; define richer policy during overhaul if HTML remains supported. | P2 | Add the normalization fixture to an automated test runner when test infrastructure is introduced.
US-019 | Topics | Heading click topic drilldown | As a researcher, I want to click a response heading to create a deeper topic-specific Wabbit Trail response. | Markdown heading click uses the response card's original model/provider, sets topic loading, calls generateTopicResponse or fallback generateResponse with researchSystemPrompt, appends topic metadata, and resets loading. | src/components/MarkdownMessage.tsx; src/lib/topicHandler.ts | Verified | Post-fix browser test clicked the Follow-up topic heading, appended an active Wabbit Trail response, preserved previous query/model context, and logged no warnings/errors. npm run verify:user-stories also covers topic native/fallback/error paths. |  | P1 | Add mock provider response with headings and verify topic metadata/model choice.
US-020 | Errors | Provider error rendering | As a user, I want provider/setup failures to show as response cards so I can see what failed instead of losing my query. | QueryInput catches provider/setup errors, appends a Response whose body starts 'Error: Failed to generate response', leaves the query available for retry, and resets loading. | src/components/QueryInput.tsx; src/components/MarkdownMessage.tsx | Verified | Final no-mock browser test on http://127.0.0.1:5183/ rendered exactly one handled missing-key error card with no duplicate MarkdownMessage warning. | No retry button or structured error state yet. | P2 | Design explicit error actions before overhaul UI work.
US-021 | Environment | Environment variable configuration | As a developer, I want a fresh checkout to explain missing API keys gracefully so setup issues are recoverable. | A missing provider key should not crash app startup; submitting with a missing key should create a recoverable error response; .env.example should contain placeholders only. | src/api/openRouter.ts; src/api/gemini.ts; .env.example | Verified | Final no-mock app loaded successfully. Missing-key submit rendered a local provider setup error response. .env.example uses placeholders only; final env check found both VITE_OPENROUTER_API_KEY and VITE_GEMINI_API_KEY missing. | If the previous example key was real, rotation remains outside this repo change. | P0 | Rotate/verify any exposed key externally if it was real.
US-022 | Tooling | Build and lint scripts | As a developer, I want build and lint scripts to validate the app before overhaul work starts. | npm run build compiles TypeScript/Vite; npm run lint runs the ESLint flat config including .mjs scripts and React hooks rules; strict TypeScript no-unused audit and npm run verify:user-stories pass. | package.json; eslint.config.js; tsconfig.node.json | Verified | Final npm run build, npm run lint, npx tsc --noEmit --noUnusedLocals true --noUnusedParameters true, npm run verify:user-stories, npm outdated --json, npm audit --json, and stale/deprecated source scans all pass. |  | P1 | Confirm dependency updates before package changes.
US-023 | App Shell | Next.js exploration workspace shell | As an explorer, I want Wabbit to open directly into a graph workspace so I can start exploring without a landing page. | The app renders the Wabbit header, trail, canvas, inspector, command bar, model route selector, and disabled Run button before prompt entry. | app/page.tsx; src/components/WorkspaceShell.tsx; browser verification on http://127.0.0.1:55234/ | Verified | Browser QA: initial load showed shell, empty graph, inspector, model route selector, and disabled Run state. |  | P0 | Keep as primary app shell; remove legacy Vite shell in a confirmed cleanup pass.
US-024 | AI Runtime | Server-side AI route with mock and Gateway routes | As an explorer, I want model runs to go through the product server so provider credentials stay out of browser code. | The browser posts to /api/ai/run; route validates payload size and route ID; mock runs complete without provider credentials; Gateway runs require server AI_GATEWAY_API_KEY/OIDC. | app/api/ai/run/route.ts; src/server/ai/*; src/lib/models.ts | Verified | npm run verify:user-stories; npx tsc --noEmit --noUnusedLocals true --noUnusedParameters true; npm run build | Live Gateway not exercised because no production provider call was required. | P0 | Add auth/rate limiting before any public unauthenticated deployment.
US-025 | Exploration Graph | Prompt-to-response graph session | As an explorer, I want prompts and responses to become linked graph nodes so I can inspect how the exploration developed. | Submitting a prompt creates a prompt node, response node, edge, provider state, selected response, markdown content, and route metadata. | src/domain/exploration.ts; src/hooks/useExplorationWorkspace.ts; src/components/canvas/* | Verified | Browser QA: mock prompt created prompt and response nodes; verifier covers prompt run and graph adapter. |  | P0 | Add durable multi-device storage only after local session model is accepted.
US-026 | Topic Branching | Clickable heading drilldown | As an explorer, I want a response heading click to create a linked topic branch so I can pursue follow-up ideas without losing context. | Clicking a rendered heading submits a topic request with parent query/context and creates topic prompt and response nodes linked to the parent response. | src/components/InspectorPanel.tsx; src/hooks/useExplorationWorkspace.ts; src/domain/exploration.ts | Verified | Browser QA: clicking Follow-up angle added topic prompt/response branch; verifier covers topic run edge. |  | P0 | Keep heading click behavior as preserved parity from the old markdown flow.
US-027 | Artifacts | User-controlled artifact promotion | As an explorer, I want suggested concepts/entities to be promotable so useful structure becomes graph state only when I choose it. | Inspector shows suggested artifacts from response content; clicking a suggestion creates a typed artifact node linked to the source response and selects it. | src/domain/exploration.ts; src/components/InspectorPanel.tsx | Verified | Browser QA: promoted AI Gateway concept; verifier covers artifact promotion. |  | P1 | Expand artifact schemas after concept/entity cards prove useful.
US-028 | Persistence | Local session persistence adapter | As an explorer, I want the current private session to survive reloads so I can continue a local exploration. | Session state is loaded from browser storage, saved after mutations, and resets to a fresh session if storage is unavailable or invalid. | src/lib/explorationStore.ts; src/hooks/useExplorationWorkspace.ts | Verified | npm run verify:user-stories covers roundtrip, invalid JSON fallback, and clear behavior. | Browser reload persistence was not manually checked after artifact promotion. | P1 | Manual reload QA before replacing local storage with durable persistence.

## Test Runs
Verification and Test Runs
Commands and browser checks executed during this baseline audit.
ID | Name | Command / Method | Result | Evidence | Date
T-001 | Production build | npm run build | Pass | TypeScript and Vite 8 build pass. Final build output chunks are all below 500 kB. | 2026-06-21
T-002 | ESLint | npm run lint | Pass | ESLint flat config passes with max-warnings=0 and React hooks rules enabled. | 2026-06-21
T-003 | Strict TypeScript | npx tsc --noEmit --noUnusedLocals true --noUnusedParameters true | Pass | Strict no-unused locals/parameters audit passes. | 2026-06-21
T-004 | No-env startup | Browser load on http://127.0.0.1:5174/ | Pass | App shell rendered without import-time provider-key crash. | 2026-06-21
T-005 | Initial UI controls | Browser DOM inventory on dummy-key server | Pass | Header, query textbox, recommended-query button, and model selector rendered with accessible names. | 2026-06-21
T-006 | Input empty/non-empty state | Browser fill and keyboard clear | Pass | Send button hidden when empty, visible after typing, hidden after keyboard clear. | 2026-06-21
T-007 | Recommended query dropdown | Browser menu interaction | Pass | Menu displayed hardcoded suggestions; selecting one immediately submitted and rendered a mock response as coded. | 2026-06-21
T-008 | Dummy OpenRouter error | Selected recommendation with dummy key | Pass | OpenRouter returned 401 and app rendered a handled error card. No real key was used. | 2026-06-21
T-009 | Model selector | Browser dialog/tab/radio checks | Pass | OpenRouter tab defaults and three OpenRouter radio options verified. | 2026-06-21
T-010 | Gemini selector/config | Browser Gemini tab/config checks | Pass | Five Gemini options, inline config region, maxOutputTokens=1234 propagation, and Done close behavior verified. | 2026-06-21
T-011 | No-env missing-key submit | Browser submit on no-env server | Pass | Rendered one local missing-key error card without duplicate warning from MarkdownMessage. | 2026-06-21
T-012 | Multi-card responses | Two no-env submissions | Pass | Two response cards rendered with query, timestamp, model, and error body. | 2026-06-21
T-013 | Carousel controls | Browser indicator, arrow, keyboard, drag | Pass | Indicator tabs, next arrow, ArrowLeft, inert inactive slides, and header left-drag all worked. | 2026-06-21
T-014 | Source debug-log scan | rg console/debugger/stale docs | Pass | No matches for stale docs strings, console.warn/error/log, debugger, TODO/FIXME, or exposed example key across src/docs/package files. | 2026-06-21
T-015 | Outdated dependencies | npm outdated --json | Pass | Final npm outdated returned 0 outdated packages and 0 major-version drifts after approved package updates. | 2026-06-21
T-016 | Security audit | npm audit --json | Pass | Final npm audit returned 0 vulnerabilities. | 2026-06-21
T-017 | Documentation drift scan | rg stale component/doc strings | Pass | README and technical-docs.md no longer reference removed ChatMessage/ResponseColumn/ChatContext.tsx/MarkdownService.ts names. | 2026-06-21
T-018 | Mock OpenRouter success | Browser mock-mode submit on http://127.0.0.1:5177/ | Pass | Typed query rendered OpenRouter mock response with heading, table, fenced code block, input clear, and no console errors. | 2026-06-21
T-019 | Mock Gemini success | Browser Gemini config + submit on http://127.0.0.1:5177/ | Pass | Selected Gemini 2.0 Flash-Lite, applied maxOutputTokens=1234, closed with Done, and rendered configured mock response. | 2026-06-21
T-020 | Mock topic drilldown | Browser heading click on mock response | Pass | Clicked Follow-up topic and appended active Wabbit Trail response preserving the source model. | 2026-06-21
T-021 | Markdown fixture rendering | Browser active-card DOM inspection | Pass | Headings/table/code render and node attributes do not leak; copy button is reachable and selects the rendered code text when clipboard write is unavailable. | 2026-06-21
T-022 | Delayed loading skeleton | Browser mock-mode submit on http://127.0.0.1:5182/ with VITE_MOCK_API_DELAY_MS=1200 | Pass | Loading response skeleton was visible immediately and mid-delay, then final mock response replaced it with no console errors. | 2026-06-21
T-023 | Markdown normalization fixture | Direct MarkdownService fixture via TypeScript transpile | Pass | Verified underline H1/H2 conversion, list marker spacing, table separator formatting, script stripping, indented code fencing, tilde fence conversion, and lowercase language tags. | 2026-06-21
T-024 | Deterministic user-story verifier | npm run verify:user-stories | Pass | Ten service-level checks pass for markdown normalization, model registry, Gemini config normalization, mock registry, mock response config propagation, topic native/fallback/error paths, missing-key provider factories, OpenRouter request payload/response handling, and Gemini SDK config/prompt/response handling. | 2026-06-21
T-025 | Post-fix browser smoke | Browser DOM smoke on http://127.0.0.1:5179/ with VITE_USE_MOCK_API=true | Pass | Verified recommendation select closes menu, copy fallback selects code, topic drilldown appends Wabbit Trail, Gemini config Done closes dialog, Gemini response includes maxOutputTokens=1234, and console warn/error logs stay empty. Browser screenshot capture timed out, so evidence is DOM/log based. | 2026-06-21
T-026 | Gemini invalid-config browser retest | Browser attempt on http://127.0.0.1:5180/ with VITE_USE_MOCK_API=true | Blocked | Browser backend rejected the localhost URL under URL policy. No workaround was attempted. Equivalent invalid-input behavior is covered by npm run verify:user-stories and source gates. | 2026-06-21
T-027 | Activation/root/stale-source gates | rg focused stale-handler/root scan; rg broad stale docs/debug scan; lint; strict tsc; build; verifier | Pass | No deprecated onKeyPress, fake React form event, any cast, stale JSX comment, duplicate mouse activation handler, root non-null assertion, console/debugger/TODO/FIXME, stale docs name, or exposed example key matches remain. Lint, strict TypeScript, build, and verifier pass. | 2026-06-21
T-028 | Entrypoint/template reference cleanup | rg main.jsx/vite.svg/react.svg; npm run build; npm run lint; strict tsc; verifier | Pass | index.html now points at src/main.tsx and no source/docs/index references to main.jsx, vite.svg, or react.svg remain. Build, lint, strict TypeScript, and verifier pass after the HTML change. | 2026-06-21
T-029 | Vite 8 chunk build output | npm run build after vite.config.js codeSplitting groups | Pass | Final build output splits API, markdown, Radix, vendor, React, icons, and app code into chunks below 500 kB with no caniuse-lite warning. | 2026-06-21
T-030 | Package modernization regression | npm update plus latest dependency migration; build/lint/strict tsc/verifier | Pass | React 19, Vite 8, TypeScript 6, ESLint 10, and Tailwind 4 migration completed. Build, lint, strict TypeScript, verifier, npm outdated, and npm audit pass. | 2026-06-21
T-031 | Final rendered browser loop | In-app Browser on http://127.0.0.1:5181/ with VITE_USE_MOCK_API=true | Pass | Verified app load, manual query, recommendation submit, code copy fallback, topic drilldown, carousel indicators, Previous/Next icon controls, no horizontal scroll, and clean console logs. | 2026-06-21
T-032 | No-mock missing-key behavior | Browser submit on http://127.0.0.1:5183/ without mock mode | Pass | App loaded without keys and rendered a handled provider setup error card for a missing OpenRouter key. | 2026-06-21
T-033 | Real provider key availability | Process/.env key inspection | Blocked | VITE_OPENROUTER_API_KEY and VITE_GEMINI_API_KEY are both missing, so successful real provider calls could not be executed. | 2026-06-21
T-034 | Provider client success contracts | npm run verify:user-stories with local axios and GoogleGenerativeAI fakes | Pass | Verified OpenRouter endpoint/payload/auth/content handling and Gemini constructor/model/generationConfig/prompt/content handling without network calls or real keys. | 2026-06-21
T-035 | Next workspace user-story verifier | npm run verify:user-stories | Pass | 7 deterministic user-story checks passed: markdown, model routes, prompt graph, topic branch, validation, persistence, graph layout. | 2026-07-01
T-036 | Next workspace strict TypeScript | npx tsc --noEmit --noUnusedLocals true --noUnusedParameters true | Pass | No TypeScript errors after Next migration and server/client split. | 2026-07-01
T-037 | Next workspace ESLint | npm run lint | Pass | ESLint and Prettier rules pass across app, src, scripts, and config files. | 2026-07-01
T-038 | Next production build | npm run build | Pass | Next.js 16.2.9 Turbopack build passes; / is static and /api/ai/run is dynamic. | 2026-07-01
T-039 | Browser exploration smoke test | In-app browser on http://127.0.0.1:55234/ | Pass | Loaded workspace; submitted mock prompt; clicked Follow-up angle; promoted AI Gateway artifact; no console warnings/errors. | 2026-07-01
T-040 | Dependency outdated scan | npm outdated --json | Warn | Patch/minor drift remains for Radix packages, @types/node, @typescript-eslint, eslint, lucide-react, postcss, and prettier. | 2026-07-01
T-041 | Dependency audit scan | npm audit --json | Warn | 2 moderate advisories reported against next via nested postcss; npm fix suggestion points to an invalid major downgrade path and needs manual triage. | 2026-07-01
T-042 | Expanded Next workspace verifier | npm run verify:user-stories | Pass | 12 deterministic checks passed, including recommended prompts plus named domain, runRequest, persistence, and graph adapter test modules. | 2026-07-01
T-043 | Secret-boundary source and bundle scan | rg against .next/static and client-importable app/src paths | Pass | No AI_GATEWAY_API_KEY, VITE provider keys, provider SDK, generateText, or server-only process.env access found in client bundle/client-importable modules. | 2026-07-01
T-044 | Route abuse controls | POST /api/ai/run with unknown route and oversized prompt | Pass | Unknown route returned 404 safe JSON; 8001-character prompt returned 400 safe JSON before provider execution. | 2026-07-01
T-045 | Responsive command workspace smoke | In-app browser desktop and 390x844 mobile viewport | Pass | Recommended prompt submitted through command flow; graph/inspector/artifacts rendered; mobile viewport had scrollWidth=390 and clientWidth=390 with no console warnings/errors. | 2026-07-01
T-046 | Legacy Vite/provider-client retirement scan | rg stale dependency and direct provider endpoint scans | Pass | No Vite plugin imports, removed provider SDK imports, direct OpenRouter/Gemini endpoints, browser provider key variables, or provider Authorization headers remain in app/src/config/docs. | 2026-07-01

## Defects Risks
Defects, Risks, and Overhaul Backlog
Prioritized issues found from source review, commands, and browser checks.
ID | Priority | Area | Status | Issue | Evidence | Recommended Action
D-001 | P0 | Environment | Fixed | Provider API modules threw at import time when keys were missing. | src/api/openRouter.ts; src/api/gemini.ts | Validation moved to factory/request time; no-env startup passes.
D-002 | P0 | Environment | Fixed | .env.example contained an actual-looking Gemini key. | .env.example | Replaced with placeholder. Rotate externally if the prior value was real.
D-003 | P0 | Tooling | Fixed | ESLint could not use the legacy config. | eslint.config.js; npm run lint | Added flat config; lint passes.
D-004 | P0 | Gemini | Fixed | Gemini config dialog did not affect generation options. | src/components/QueryInput.tsx; src/interfaces/core.ts | QueryInput now passes geminiConfig for Gemini requests.
D-005 | P0 | API | Fixed | GeminiApiClient constructor apiKey was unused. | src/api/gemini.ts | Client constructs GoogleGenerativeAI with the provided key.
D-006 | P1 | Responses | Fixed | Topic handling used current selected model instead of response.model. | src/components/MarkdownMessage.tsx | Topic handler now uses the response card's model.
D-007 | P1 | Carousel | Fixed | Header drag was unwired and drag direction used an absolute X coordinate. | src/components/ResponseList.tsx; src/components/CardCarousel.tsx; src/components/ChatResponseCard.tsx | Drag props now reach the card and signed drag distance controls navigation; browser drag test passes.
D-008 | P1 | Accessibility | Fixed | Icon-only action buttons lacked accessible labels. | src/components/QueryInput.tsx; src/components/ModelSelector.tsx; src/components/GeminiConfigDialog.tsx | Added aria-labels for recommendations, send, model selector, and Gemini config.
D-009 | P2 | Logging | Fixed | API key prefixes and handled provider errors were logged to console. | src/api/openRouter.ts; src/components/QueryInput.tsx; src/lib/topicHandler.ts | Removed key/debug logging from handled paths.
D-010 | P2 | Code Health | Fixed | Strict no-unused audit found dead imports/fields and duplicate action type. | npx tsc --noEmit --noUnusedLocals true --noUnusedParameters true | Cleaned unused imports/fields; strict TypeScript passes.
D-011 | P2 | CSS | Fixed | Vite template CSS/assets remained unused. | src/index.css; src/assets/react.svg; public/vite.svg; index.html | Removed unused template CSS, Vite favicon reference, public/vite.svg, and src/assets/react.svg after confirmation.
D-012 | P2 | Docs | Fixed | README was the default Vite template and technical docs mentioned removed files. | README.md; technical-docs.md | README and technical-docs.md updated; stale-reference rg scan now passes.
D-013 | P2 | Markdown | Fixed | Heading topic text was poor for formatted heading children. | src/components/markdown/EnhancedMarkdown.tsx | Added recursive React child text extraction and keyboard activation.
D-014 | P1 | Gemini Config | Fixed | Nested Gemini config dialog was hard to activate reliably and could exceed the viewport. | src/components/GeminiConfigDialog.tsx; src/components/ModelSelector.tsx | Replaced nested modal with inline config region, constrained model dialog scrolling, and verified maxOutputTokens=1234 reaches mock Gemini responses.
D-015 | P1 | Security | Fixed | npm audit reported vulnerable direct/transitive dependencies. | npm audit --json | Approved dependency modernization reduced final npm audit to 0 vulnerabilities.
D-016 | P1 | Dependencies | Fixed | Many dependencies were stale. | npm outdated --json | Approved dependency modernization reduced final npm outdated to 0 outdated packages and 0 major-version drifts.
D-017 | P1 | Tooling | Fixed | React hooks linting was not active because older plugin/config combinations were incompatible. | eslint.config.js; npm run lint | Updated ESLint/tooling, removed incompatible eslint-plugin-react, enabled eslint-plugin-react-hooks rules, and fixed hook dependency findings.
D-018 | P1 | Testing | Fixed | Successful provider calls and topic drilldown lacked deterministic runtime coverage. | src/api/mock.ts; Browser tests; src/services/markdown/MarkdownNormalizer.ts; scripts/verify-user-stories.mjs | Mock provider harness and deterministic verifier now cover OpenRouter/Gemini provider success contracts, mock responses, Gemini config propagation, markdown rendering, recommendations, loading skeletons, copy fallback, topic drilldown, and markdown normalization. Real provider key availability is tracked separately by T-033.
D-019 | P2 | Build | Fixed | Build warned about stale caniuse-lite. | npm run build | Dependency modernization removed the stale caniuse-lite warning; final build is clean.
D-020 | P2 | Product UX | Watch | Recommended query selection immediately submits. | src/components/QueryInput.tsx; browser test | Keep if intended; otherwise change to populate input first.
D-021 | P2 | Markdown | Fixed | Code block copy button previously ended at Copy failed when browser clipboard writing was unavailable. | src/components/markdown/EnhancedMarkdown.tsx; Browser copy test | Fallback now selects the rendered code block and shows Selected; Browser test verified selected text matches the mock code block.
D-022 | P2 | Dialog UX | Fixed | Dialog icon close hit testing landed on the SVG path instead of the close button. | src/components/ui/dialog.tsx | Added pointer-events-none to dialog close SVG; hit testing now targets the close button. Model selector also has an explicit Done action.
D-023 | P1 | Dropdown UX | Fixed | Recommended-query dropdown stayed visibly rendered after selection even when Radix marked it closed. | src/components/QueryInput.tsx; src/components/ui/dropdown-menu.tsx | Recommendation menu is controlled and shared dropdown content now hides when data-state=closed; post-fix browser smoke verifies the menu is gone after selection.
D-024 | P1 | Dialog UX | Fixed | Model selector dialog stayed visibly rendered after Done even when Radix marked it closed. | src/components/ui/dialog.tsx; src/components/ModelSelector.tsx | Shared dialog overlay/content now hide when data-state=closed; post-fix browser smoke verifies Done removes the visible dialog and Gemini submit still works.
D-025 | P2 | Gemini Config | Fixed | Gemini numeric configuration accepted invalid or out-of-range typed values before apply. | src/lib/geminiConfig.ts; src/components/GeminiConfigDialog.tsx; scripts/verify-user-stories.mjs | Added pure config normalization for defaults, clamps, integer rounding, and empty/invalid fallback. npm run verify:user-stories covers this contract.
D-026 | P2 | Code Health | Fixed | Query input used deprecated onKeyPress and recommended-query submit fabricated a React event object. | src/components/QueryInput.tsx | Replaced with onKeyDown and a shared submitQuery helper for manual and recommended submissions.
D-027 | P2 | Dialog UX | Fixed | Model selector Done and Gemini Apply carried duplicate pointer/mouse activation paths. | src/components/ModelSelector.tsx; src/components/GeminiConfigDialog.tsx | Simplified to one click path plus explicit Enter/Space keyboard handling so close/apply state changes cannot fire from parallel mouse handlers.
D-028 | P2 | App Shell | Fixed | The app root mount used a non-null assertion against #root. | src/main.tsx | Added an explicit root lookup guard with a clear startup error before ReactDOM.createRoot.
D-029 | P3 | Code Health | Fixed | The import compatibility declaration file contained stale JSX-resolution comments and declarations for removed components. | src/import-path-fix.d.ts | Updated the comment to describe current extensionless local import declarations and removed stale ChatMessage/ResponseColumn declarations.
D-030 | P2 | App Shell | Fixed | index.html still referenced the removed src/main.jsx entrypoint and default Vite favicon. | index.html | Updated the module script to /src/main.tsx and removed the /vite.svg favicon link; stale entrypoint/template reference scans now pass.
D-031 | P2 | Build | Fixed | The production bundle emitted one JavaScript chunk above Vite's 500 kB warning threshold. | vite.config.js; npm run build | Migrated to Vite 8 codeSplitting groups for API, markdown, Radix, vendor, React, icons, and app code; rebuilt chunks are all below 500 kB.
D-032 | P1 | Framework Migration | Fixed | React, Vite, TypeScript, Tailwind, and ESLint major updates required migration work. | package.json; vite.config.js; tailwind.config.js; src/index.css; tsconfig.json; eslint.config.js | Migrated to React 19, Vite 8, TypeScript 6, Tailwind 4 Vite plugin, and ESLint 10 while preserving build, lint, strict TypeScript, and rendered behavior.
D-033 | P2 | API Errors | Fixed | Provider API wrappers dropped original error causes. | src/api/gemini.ts; src/api/openRouter.ts | Wrapped provider errors with ErrorOptions.cause so callers keep the original failure context.
D-034 | P1 | Carousel UX | Fixed | Carousel overflow could create hidden horizontal scroll and make navigation arrows invisible or unclickable. | src/components/ResponseList.tsx; browser layout tests | Moved horizontal clipping to the carousel viewport, rendered nav buttons in a stable row with fixed placeholders, and verified Previous/Next clickability with responseScrollLeft=0 and no document horizontal scroll.
D-035 | P1 | Architecture | Open | Legacy chat, Vite, and compatibility modules still exist in source for compile-safe migration. | technical-docs.md Known Legacy Surface; src/components legacy chat files; src/main.tsx; vite.config.js; index.html | Remove legacy surface in a confirmed cleanup pass after workspace acceptance.
D-036 | P1 | Dependencies | Open | npm outdated shows patch/minor drift after stack migration. | npm outdated --json on 2026-07-01 | Batch low-risk patch updates separately; verify full gates after update.
D-037 | P1 | Security | Open | npm audit reports 2 moderate advisories through next nested postcss. | npm audit --json on 2026-07-01 reports next affected via postcss <8.5.10 in node_modules/next/node_modules/postcss. | Monitor Next patch availability or upstream advisory resolution; do not apply npm suggested downgrade.
D-038 | P1 | Deployment Security | Open | The AI run route assumes private/protected deployment and does not yet include auth or rate limiting. | docs/plans KTD8; app/api/ai/run/route.ts validates size/routes but no user auth. | Add auth/rate limit before public unauthenticated deployment.
D-039 | P0 | Security | Fixed | Browser-exposed VITE provider key pattern conflicted with secure AI runtime requirements. | .env.example now documents AI_GATEWAY_API_KEY as server-only; app/api/ai/run/route.ts owns AI execution. | Keep provider credentials server-only; do not add NEXT_PUBLIC provider keys.
D-040 | P0 | Security | Fixed | Client-importable providerConfig read a server-only mock env and legacy public provider-key names during compatibility migration. | src/lib/providerConfig.ts; secret-boundary rg scans on 2026-07-01 | ProviderConfig now reads only NEXT_PUBLIC_WABBIT_USE_MOCK_API and never exposes provider credentials or server-only AI Gateway values.
D-041 | P1 | Architecture | Fixed | Legacy Vite config and browser provider clients still referenced removed packages or direct provider endpoints after the Next migration. | vite.config.js; src/api/openRouter.ts; src/api/gemini.ts; rg stale dependency scans on 2026-07-01 | Vite config is now a retired stub and legacy provider factories use the product server AI route compatibility client.

## Dependencies
Outdated Dependencies and npm Audit
Generated from npm outdated --json and npm audit --json on 2026-06-21.
Type | Package | Current | Wanted | Latest | Major Drift | Audit Severity | Advisory Summary
Outdated | @radix-ui/react-dialog | 1.1.17 | 1.1.18 | 1.1.18 | No |  | Patch drift after migration.
Outdated | @radix-ui/react-dropdown-menu | 2.1.18 | 2.1.19 | 2.1.19 | No |  | Patch drift after migration.
Outdated | @radix-ui/react-label | 2.1.10 | 2.1.11 | 2.1.11 | No |  | Patch drift after migration.
Outdated | @radix-ui/react-radio-group | 1.4.1 | 1.4.2 | 1.4.2 | No |  | Patch drift after migration.
Outdated | @radix-ui/react-slider | 1.4.1 | 1.4.2 | 1.4.2 | No |  | Patch drift after migration.
Outdated | @radix-ui/react-tabs | 1.1.15 | 1.1.16 | 1.1.16 | No |  | Patch drift after migration.
Outdated | @types/node | 26.0.0 | 26.0.1 | 26.0.1 | No |  | Patch drift after migration.
Outdated | @typescript-eslint/eslint-plugin | 8.61.1 | 8.62.1 | 8.62.1 | No |  | Minor drift after migration.
Outdated | @typescript-eslint/parser | 8.61.1 | 8.62.1 | 8.62.1 | No |  | Minor drift after migration.
Outdated | eslint | 10.5.0 | 10.6.0 | 10.6.0 | No |  | Minor drift after migration.
Outdated | lucide-react | 1.21.0 | 1.22.0 | 1.22.0 | No |  | Minor drift after migration.
Outdated | postcss | 8.5.15 | 8.5.16 | 8.5.16 | No |  | Patch drift after migration.
Outdated | prettier | 3.8.4 | 3.9.4 | 3.9.4 | No |  | Minor drift after migration.
Audit | next | 16.2.9 |  |  | No | moderate | npm audit reports next affected through nested postcss; suggested fix is invalid downgrade and requires manual triage.
Audit | postcss | next nested dependency |  |  | No | moderate | GHSA-qx2v-qp2m-jg93 via node_modules/next/node_modules/postcss <8.5.10.
Outdated 2026-07-01 | @radix-ui/react-dialog | 1.1.17 | 1.1.18 | 1.1.18 | No |  | Patch drift after Next workspace migration.
Outdated 2026-07-01 | @radix-ui/react-dropdown-menu | 2.1.18 | 2.1.19 | 2.1.19 | No |  | Patch drift after Next workspace migration.
Outdated 2026-07-01 | @radix-ui/react-label | 2.1.10 | 2.1.11 | 2.1.11 | No |  | Patch drift after Next workspace migration.
Outdated 2026-07-01 | @radix-ui/react-radio-group | 1.4.1 | 1.4.2 | 1.4.2 | No |  | Patch drift after Next workspace migration.
Outdated 2026-07-01 | @radix-ui/react-slider | 1.4.1 | 1.4.2 | 1.4.2 | No |  | Patch drift after Next workspace migration.
Outdated 2026-07-01 | @radix-ui/react-tabs | 1.1.15 | 1.1.16 | 1.1.16 | No |  | Patch drift after Next workspace migration.
Outdated 2026-07-01 | @types/node | 26.0.0 | 26.0.1 | 26.0.1 | No |  | Patch drift after Next workspace migration.
Outdated 2026-07-01 | @typescript-eslint/eslint-plugin | 8.61.1 | 8.62.1 | 8.62.1 | No |  | Minor drift after Next workspace migration.
Outdated 2026-07-01 | @typescript-eslint/parser | 8.61.1 | 8.62.1 | 8.62.1 | No |  | Minor drift after Next workspace migration.
Outdated 2026-07-01 | eslint | 10.5.0 | 10.6.0 | 10.6.0 | No |  | Minor drift after Next workspace migration.
Outdated 2026-07-01 | lucide-react | 1.21.0 | 1.22.0 | 1.22.0 | No |  | Minor drift after Next workspace migration.
Outdated 2026-07-01 | postcss | 8.5.15 | 8.5.16 | 8.5.16 | No |  | Patch drift after Next workspace migration.
Outdated 2026-07-01 | prettier | 3.8.4 | 3.9.4 | 3.9.4 | No |  | Minor drift after Next workspace migration.
Audit 2026-07-01 | next | 16.2.9 |  |  | No | moderate | npm audit reports next affected through nested postcss; suggested fix is invalid downgrade and requires manual triage.
Audit 2026-07-01 | postcss | next nested dependency |  |  | No | moderate | GHSA-qx2v-qp2m-jg93 via node_modules/next/node_modules/postcss <8.5.10.

## Code Inventory
Code Inventory
Source files grouped by responsibility for the overhaul baseline.
Path | Module | Behavior / Responsibility | Category
index.html | HTML shell | Root DOM container and src/main.tsx module entrypoint | User-facing
vite.config.js | Vite config | React plugin, Tailwind 4 Vite plugin, path alias, and Vite 8 production codeSplitting groups | Tooling
src/main.tsx | React entrypoint | Root element guard and React app mount | User-facing
src/import-path-fix.d.ts | Compatibility declarations | Extensionless local component import declarations | Tooling
src/App.tsx | Root app shell | Header and main ChatInterface mount | User-facing
src/components/ChatInterface.tsx | Chat workspace container | Wraps InputArea and ResponseList in ChatProvider | User-facing
src/components/ChatContextProvider.tsx | State provider | Responses, selected model, loading flags, Gemini config, active index | State
src/hooks/useChatContext.ts | Context hooks | useChatState and useChatDispatch guards | State
src/components/InputArea.tsx | Input container | Card containing QueryInput and ModelControls | User-facing
src/components/QueryInput.tsx | Prompt entry | Manual input, recommended prompts, provider dispatch, error response | User-facing
src/components/ModelControls.tsx | Model control bridge | Connects context to ModelSelector | User-facing
src/components/ModelSelector.tsx | Provider/model dialog | OpenRouter and Gemini tabs/radio groups | User-facing
src/components/GeminiConfigDialog.tsx | Gemini inline config region | Temperature/topK/topP/maxOutputTokens controls | User-facing
src/components/ResponseList.tsx | Response carousel container | Cards, loading skeleton, arrows, indicator tabs | User-facing
src/components/CardCarousel.tsx | Carousel engine | Stacking transforms, keyboard/wheel/autoplay/drag support | User-facing
src/components/ChatResponseCard.tsx | Response card | Query/topic header, timestamp, model, markdown body, drag source | User-facing
src/components/MarkdownMessage.tsx | Markdown/topic bridge | EnhancedMarkdown plus heading topic click handling | User-facing
src/components/markdown/EnhancedMarkdown.tsx | Markdown renderer | ReactMarkdown GFM, clickable headings, copyable code, tables, links | User-facing
src/components/ResponseSkeleton.tsx | Loading placeholder | Skeleton for pending normal/topic responses | User-facing
src/services/markdown/MarkdownNormalizer.ts | Markdown normalization service | Heading/list/table/script/code normalization | Service
src/lib/topicHandler.ts | Topic drilldown handler | Creates topic responses with research prompt and metadata | Service
src/lib/prompts.ts | Prompt constants | Research system prompt for topic drilldown | Service
src/lib/models.ts | Model registry | OpenRouter/Gemini model definitions and lookup helpers | Service
src/lib/geminiConfig.ts | Gemini config normalization | Defaults, clamps, integer rounding, and invalid-input fallback for Gemini controls | Service
src/services/api/ApiClientRegistry.ts | API registry | Registers and caches provider clients | Service
src/api/openRouter.ts | OpenRouter client | Chat completions API integration | Service
src/api/gemini.ts | Gemini client | Google Generative AI integration | Service
src/components/ui/* | shadcn/Radix primitives | Buttons, dialogs, menus, inputs, labels, radio group, slider, tabs, cards | UI Infrastructure
src/index.css | Global styles | Tailwind 4 import/config, theme variables, carousel, markdown styles | UI Infrastructure
tailwind.config.js | Tailwind config | ES module Tailwind 4-compatible app content/theme/plugin config | Tooling
scripts/verify-user-stories.mjs | Deterministic user-story verifier | Node-based checks for service contracts without browser, network, or provider calls | Tooling
eslint.config.js | ESLint flat config | JS/TS/React hooks/Prettier lint rules | Tooling
package.json | Scripts/dependencies | dev/build/lint/preview and package inventory | Tooling